## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Identify Tablets and Secure Vendors |  |  |  | 17
Idenitfy potential tablet models and software packages |  |  |  | 1
Contact Terrific Tablets Marketing Department |  |  |  | 1
Select a custom menu branding, design, and upload package |  |  |  | 1
Create contracts and statements of work for vendors |  |  |  | 2
Determine # of tablets needed for each location | May have less tablets than planned at launch due to supply issues |  |  | 1
Ship the tablets to the locations | Updated tablets are currently delayed due to a storm. Current model tablets will be shipped from distant warehouse, adding 3-4 days to initial 7 day estimate |  |  | 11
Milestone: Designing Menu and Coupons |  |  |  | 8
Design mockup menus and coupons | Carter will need to finish menu redesign |  |  | 7
Upload mock ups | 3-4 hours once mock ups are received |  |  | 1
Milestone: Tablet Installation |  |  |  | 4
Hire an electrician to wire tables | Will need to do a half day at each location, possible schedule conflicts |  |  | 2
Install tablets in the bar area | Install usually happens day after delivery. |  |  | 1
Swap tablets once new models available | New models delayed by supply chain issues. Swap is simple plug change. |  |  | 1
Milestone: Integrate Existing Software and Payments with Tablets |  |  |  | 10
Work with POS Vendor to integrate POS software with tablets |  |  |  | 1
Update POS software if necessary | May introduce delays and has never been attempted |  |  | 3
Develop payment methods (contactless, mobile payment, etc.) |  |  |  | 2
Integrate inventory management software with tablets |  |  |  | 2
Develop plan for tracking metrics |  |  |  | 2
Milestone: Train Staff and Secure Buy-in |  |  |  | 11
Prepare and plan trainings | General training a common occurence |  |  | 7
Pre-training staff meeting to introduce tablets and secure buy-in |  |  |  | 1
Conduct small training with GMs and managers |  |  |  | 1
Conduct follow up training with waitstaff and kitchen staff | Have never had to train waitstaff on software, could add time |  |  | 2
Milestone: Final Testing and Launch Prep |  |  |  | 3
Invite friends and family for a testing session |  |  |  | 1
Create launch day plan |  |  |  | 1
Advertise menu tablets on social media |  |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Identify Tablets and Secure Vendors
Idenitfy potential tablet models and software packages
Contact Terrific Tablets Marketing Department
Select a custom menu branding, design, and upload package
Create contracts and statements of work for vendors
Determine # of tablets needed for each location | May have less tablets than planned at launch due to supply issues
Ship the tablets to the locations | Updated tablets are currently delayed due to a storm. Current model tablets will be shipped from distant warehouse, adding 3-4 days to initial 7 day estimate | 11 |  |  |  | H
Milestone: Designing Menu and Coupons
Design mockup menus and coupons | Carter will need to finish menu redesign | 7 | 4 | 7 | 14 | M
Upload mock ups | 3-4 hours once mock ups are received | 1 | 0.5 | 1 | 2 | H
Milestone: Tablet Installation
Hire an electrician to wire tables | Will need to do a half day at each location, possible schedule conflicts | 2 | 2 | 4 | 6 | M
Install tablets in the bar area | Install usually happens day after delivery. | 1
Swap tablets once new models available | New models delayed by supply chain issues. Swap is simple plug change.
Milestone: Integrate Existing Software and Payments with Tablets
Work with POS Vendor to integrate POS software with tablets |  | 1 |  |  |  | L
Update POS software if necessary | May introduce delays and has never been attempted | 3 |  |  |  | L
Develop payment methods (contactless, mobile payment, etc.)
Integrate inventory management software with tablets
Develop plan for tracking metrics
Milestone: Train Staff and Secure Buy-in
Prepare and plan trainings | General training a common occurence | 7 |  |  |  | H
Pre-training staff meeting to introduce tablets and secure buy-in |  | 1 |  |  |  | H
Conduct small training with GMs and managers |  | 1 |  |  |  | H
Conduct follow up training with waitstaff and kitchen staff | Have never had to train waitstaff on software, could add time | 2 | 1 | 2 | 7 | L
Milestone: Final Testing and Launch Prep
Invite friends and family for a testing session
Create launch day plan
Advertise menu tablets on social media

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tablets for Restaurants: Using Tableside Tablets to Increase Sales and Decrease Costs | HERE | 2021-08-28 | If deploying electronic ordering, work with your POS vendor. You must integrate the ordering software with your POS for this implementation. Barnes noted that it can take a few extra weeks for this type of deployment compared to the view-only version of the tablet menu.
Implementing Tablet POS into your Restaurant | HERE | 2021-08-28 | Personalized Dining Experience: Tablets can provide automatic upselling opportunities, such as recommending a dessert or appetizer, and food and wine pairings for guests. Upselling is a fantastic and effortless way to increase your average check total, and your customers will appreciate and enjoy the approach.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Average ticket time of 8 minutes for appetizers | How long do customers take to get their appetizers? | Customer reports receiving appetizer in 8 minutes or less | FALSE
Customer Satisfaction | Average ticket time of 12-15 minutes for entrees | How long do customers take to get their entrees? | Customer reports receiving entree in 12-15 minutes or less | FALSE
Customer Satisfaction | Check out time of one minute or less | How long are customers taking to check out? | 90% of customers check out using the tablets instead of servers | FALSE
Customer Satisfaction | Less than 5% of customers report technical issues with the tablets | How often are customers reporting technical issues with the tablets? | Tablet error logs report a max of one error per shift. | FALSE
Customer Satisfaction | 98% order accuracy | Are customers receiving the correct orders? | 98% of customers report receiving the correct order | FALSE
Customer Satisfaction | Average wait time of 10 minutes or less | How long do customers have to wait to get a table? | Customers report waiting less than ten minutes on average | FALSE
Ease of Use | Tablets easy to use for 90+% of customers | What percent of customers report that the tablets are easy to use? | 90+% of customers report that the tablet was easy to use. | FALSE
Customer Satisfaction | Tablets increase the likelihood of future visits by 20% | What percent of customers say the tablets are more likely to make them return to the restaurant? | 20% of customers report being more lilkey to visit in the future because of the tablets. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time of 8 minutes for appetizers | How long do customers take to get their appetizers? | Customer reports receiving appetizer in 8 minutes or less | How long did it take for you to receive your appetizers? | Multiple choice | 0-5 minutes | 5-8 minutes | 8-12 minutes | 12 or more minutes | I did not order an appetizer
Average ticket time of 12-15 minutes for entrees | How long do customers take to get their entrees? | Customer reports receiving entree in 12-15 minutes or less | How long did it take for you to receive your entrees? | Multiple choice | 5-8 minutes | 8-12 minutes | 12-15 minutes | 15 or more minutes | I did not order an entree
Check out time of one minute or less | How long are customers taking to check out? | 90% of customers check out using the tablets instead of servers | How long did it take for you to checkout using the menu tablet? | Multiple choice | less than 30 seconds | 30 seconds to 1 minute | 1-2 minutes | 2 or more minutes | I did not check out using a menu tablet
Less than 5% of customers report technical issues with the tablets | How often are customers reporting technical issues with the tablets? | Tablet error logs report a max of one error per shift. | Did you have any technical issues using the menu tablet? | Yes/No | Yes | No
98% order accuracy | Are customers receiving the correct orders? | 98% of customers report receiving the correct order | Was your order delivered correctly the first time? | Yes/No | Yes | No
Average wait time of 10 minutes or less | How long do customers have to wait to get a table? | Customers report waiting less than ten minutes on average | Approximately how long did it take for you to be seated? | Open-ended | Customer will be asked to input a number
Tablets easy to use for 90+% of customers | What percent of customers report that the tablets are easy to use? | 90+% of customers report that the tablet was easy to use. | On a scale of very difficult to very easy, how would you rate how easy it was to use the menu tablet? | Scaled | Very Difficult | Difficult | No Opinion | Easy | Very Easy
Tablets increase the likelihood of future visits by 20% | What percent of customers say the tablets are more likely to make them return to the restaurant? | 20% of customers report being more lilkey to visit in the future because of the tablets. | True or false, the menu tablets make it more likely that you will visit Sauce and Spoon again in the future? | True/False | TRUE | FALSE